## Slide 1: Intro. To Software Development Final Project
Ethan Boileau, Julian Wemmie, Patrick Foster, Avi Kaufman

## Slide 2: Overview
This PowerPoint will go over the tasks that need to be done to complete the project, how roles are designated among the group members, our rationale for our decision making, and the in order we will approach each Sprint.
Overview
Programming Task
Miscellaneous Tasks
Sprint 2 plan
Sprint 3 plan

## Slide 3: Programming Tasks
Complete the ReliabilityAnalysis.java class (Complete by April 20th)
  Reliability Analysis will need to have the methods getReliabilities and verifyReliabilties implemented with three additional helper functions.
  Get Reliabilities will implement an algorithm that take in the workload and return the RelaibilityTable of the correct output.
Complete the ReliabilityVisualization.java class (Complete by April 25th)
  The initialize method will call Reliability Analysis to get the Reliability table then will format is as a Description Object to be used in creation of the “.ra” file.
These classes will need to be completed with methods that will allow for the creation of “.ra” files, an output file that shows the various parameters for input and the output of end-to-end reliability for each flow.

## Slide 4: Diagram Tasks
Complete a UML Sequence Diagram (Complete by April 10th)
  The sequence diagram will give a visual representation of how the final product will work. It will follow the elements of the program at the beginning of the execution, through the end where it outputs. It will list all the elements and how they will interact with each other in the program.
  It will showcase the interaction between different objects.
UML Diagrams (Complete by April 15th)
  Changes in methods and attributes in Reliability Visualization and Reliability Analysis will be reflected in their UML Diagrams.

## Slide 5: Codebase Sustainability Tasks
JavaDocs (Completed by April 25th)
  New methods and attributes with have Javadoc compliant documentation.
  Documentation will be made before the implementation of the methods
JUnit tests (Completed by April 13th)
  Many thorough tests will be used to ensure sustainability throughout the codebase and prevent errors from getting pushed to production in future changes
  Unit tests will be written before implementing the methods to follow Test Driven Development.

## Slide 6: Sprint 2 - Task Order and Duties
ReadMe File (Ethan)
JUnit Test (Julian)
Update UML Diagram (Avi)
Write Java Docs (Ethan)
Implement three methods in Visualization (Patrick)
  Initialize
  Visualization
  createHeader
  createFooter
Plan for next sprint (All)

## Slide 7: Sprint 3 - Task Order and Duties
ReadMe File (Ethan)
JUnit Test (Patrick)
Update UML Diagram (Ethan)
Write Java Doc (Ethan)
Implement five methods in ReliabilityAnalysis (Avi and Julian)
  getReliabilities
  verifyReliabilities
  Helper methods 1-3